## Sheet1
(ORGANIZATION NAME) |  | XYZ
This risk assessment is aligns with: |  |  | ISO 27001
Objective: |  |  | Risk Assessment (Risk Register)
Date of the risk assessment: |  |  | <date>
Version |  |  | 1
Risk should be reassessed periodically throughout the life of the program or project.
Document Author |  |  | <Name>
Author Job Title |  |  | <Title>
Approved by |  |  | <Name>
Approver Job Title |  |  | <Title>
This risk assessment is aligns with: |  | CONTEXT (For Guidance, See Tab 3) | RISK IDENTIFICATION |  |  |  | ANALYSIS Residual risk rating with treatments in place (For Guidance, See Tab 4) |  |  |  | EVALUATION (For Guidance, See Tab 5) |  |  | TREATMENT MANAGEMENT | [5 empty] | TRACKING |  |  |  | RESIDUAL RISK RATING (Risk rating expected / predicted once all treatments, including additional treatments, are in place.) |  |  |  | CURRENT RISK RATING (Current level of risk in light of treatments implemented at this report period.) |  |  |  | RISK TOLERANCE RATING (Risk tolerance executive is willing to accept. This should be provided by executive after having been briefed on the risk, existing and planned treatments, and associated costs.)
RISK # | CATEGORY | BUSINESS OBJECTIVE/ PRIORITY | RISK EVENT | RISK CAUSE | IMPACT | CURRENT TREATMENTS | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | ADEQUACY OF CURRENT TREATMENTS | ACTION | TREND | ADDITIONAL PLANNED TREATMENT | DELIVERABLES | TASK OWNER | DUE DATE | DEPENDENCIES/ INTER-RELATIONSHIPS | STATUS | PROGRESS % | COMMENTS/ ISSUES | FURTHER ACTION | COMPLETION DATE | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP | L (1-5) | C (1-5) | RISK RATING | HEAT MAP
Add identifiers to better organize and track risks. | Which category does this Risk Event fall under? | What business objective/priority does this Risk Event affect (e.g., Mandate letter, strategic directive, etc.)? | What events could impact the achievement of objectives (can be positive or negative)? | What Risk Cause (trigger, circumstance, uncertainty) could increase the Likelihood of the Risk Event occurring? There are usually multiple Risk Causes leading to a Risk Event. | How would the Risk Event impact the achievement of the objective/priority? | What Treatments are currently in place to manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | How likely? | How severe? | (LxC) | Rating with current treatments in place | Non-existent Inadequate Adequate Robust | Will you do more to manage the risk (treat) or choose to accept and monitor? | If applicable, has this risk rating changed over time? Has column J increased (upward trend), decreased (downward trend) or not changed (static) | What Treatments are needed to further manage the Risk Event? Focus on Treatments that either reduce the Likelihood (column H) of the Risk Event or can reduce the Consequence (column I) if the Risk Event occurs. | Future Treatments will come in what form (e.g., a project plan, a briefing note, report, funding request, other)? | Who will take the lead on this mitigation? | When should the deliverable be ready? (Optional) | Do the Risk Event or Treatments depend on another team or organization? Do they impact another group? | On Track Slowed Stalled |  |  |  |  | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place | How likely? | How severe? | (LxC) | Rating with current treatments in place
R1 | Phishing & Social Engineering |  | Credential compromise via phishing attack | Employee clicking on malicious link or attachment | Unauthorized access to internal systems or customer data | Basic security awareness training, Acceptable Use Policy | 4 | 4 | 16 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R2 | Malware/Ransomware |  | Systems infected with ransomware | Malicious email or software exploit | Data encryption and major operational disruption | Antivirus, intrusion detection, nightly backups | 3 | 5 | 15 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R3 | Unpatched Vulnerabilities |  | Exploitation of an unpatched system | Delayed or incomplete patch management | System compromise and data breach | Monthly patching, occasional scans | 3 | 4 | 12 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R4 | Insider Threat |  | Intentional or accidental data leak | Malicious or careless employee actions | Loss of sensitive customer data | Policies and basic awareness training | 2 | 4 | 8 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R5 | Third-Party Breach |  | Vendor security compromise | Weak third-party security controls | Exposure of FinServCo's data or disruption of services | Contractual obligations, limited oversight | 3 | 4 | 12 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R6 | Denial of Service |  | DDoS attack disrupts services | External attacker targets public-facing services | Downtime and potential customer dissatisfaction | Firewall, ISP throttling | 3 | 3 | 9 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R7 | Physical Security |  | Unauthorized physical access | Intrusion into facility or data center | Theft or tampering of IT infrastructure | CCTV, keycard access, guards | 2 | 4 | 8 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Monitor
R8 | Cloud Configuration |  | Data leak via cloud misconfiguration | Improper access controls or public exposure | Unauthorized access to sensitive data | Cloud provider default settings | 3 | 4 | 12 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
R9 | Regulatory Compliance |  | Violation of data protection laws | Policy gaps or procedural oversight | Legal penalties and reputational harm | Compliance team, regular training | 2 | 5 | 10 | MEDIUM | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Monitor
R10 | Business Continuity/DR |  | Inability to recover from major incident | Incomplete disaster recovery planning | Extended downtime, lost data | Basic response procedure, backups | 3 | 5 | 15 | HIGH | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | Treat
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED
[9 empty] | 0 | UNRATED | [15 empty] | 0 | UNRATED |  |  | 0 | UNRATED |  |  | 0 | UNRATED